Adham (Leader – hardest/most central: OO design backbone + Java architecture + integration)

Part 0 — Foundation (everyone depends on this)

A0 – Classify Use Cases + Select the 12 Core Use Cases (4 simple / 4 moderate / 4 complex)

- Use the use case diagram and classify all use cases into: simple / moderate / complex.

- Pick the final 12 (4 from each category).

- Output: classification table + list of 12 selected use cases (1–2 lines each) + rationale.

- Everyone depends on A0.

A1 – Create the Deliverable #5 “Master Template” for the Technical Report (PDF structure)

- Set report sections + numbering matching requirements.

- Output: report skeleton + where each diagram/table goes.

- Depends on A0.

Part 1 — First-Cut Design Class Diagram (step-by-step transformation)

A2 – First-Cut Design Class Diagram (Global) + Partition into Layers

- Transform from domain model to initial design classes (boundary/control/entity + data access).

- Define 3-layer architecture mapping (View/Controller/Domain/Data).

- Output: first-cut design class diagram (layered) + explanation steps.

- Depends on A0.

A3 – Integration Gate: “Design Rules” for the team

- Naming conventions, layer rules (no DB access from View/Domain), controller mediation rule, method signature style.

- Output: 1-page team design rules.

- Depends on A2.

Part 2 — Use Case Realizations (hardest ones + final merge owner)

A4 – Complex Use Cases: Multi-layer Sequence Diagrams (for 4 complex UCs)

- For each complex UC: sequence diagram including view objects + controllers + domain + DAO.

- Output: 4 sequence diagrams + identified methods/messages.

- Depends on A2/A3.

A5 – Update Design Class Diagram (Final Merge Owner)

- Collect methods from:

  - CRC (simple)

  - Communication diagrams (moderate)

  - Sequence diagrams (complex)

- Merge into final complete Design Class Diagram representing all 12 UCs.

- Output: final design class diagram (methods included) + change log summary.

- Depends on A4 + Andrew tasks (B*) + Ahmed tasks (C*) + Yassin tasks (D*).

A6 – Package Diagram for Final Design

- Group classes into packages (e.g., ui, controller, domain, dao, util).

- Output: package diagram + rationale.

- Depends on A5.

Part 3 — Implementation (Walking Skeleton + 3-layer + DB)

A7 – Model-to-Code Transformation (UML Tool) + Walking Skeleton Setup

- Generate Java code from final design class diagram (or partial skeleton early, then update).

- Create compile-able skeleton project structure.

- Output: generated code + cleaned project structure.

- Depends on A5 (or start early using A2 skeleton then update).

A8 – Implement the 2 Simple Use Cases (DB interaction) – You implement the hardest/most central plumbing

- You own:

  - DB connection strategy (SQLite/MySQL—whatever your course expects)

  - DAO base patterns

  - Controller mediation

  - Integrating with D4 UI screens

- Output: working end-to-end flow for 2 simple UCs + CRUD in DAO + UI triggers.

- Depends on D4 UI availability + B/C tasks for CRC/diagrams if they affect methods.

A9 – Technical Report Integration (Final PDF Owner)

- Merge all tables/diagrams and write rationales.

- Ensure “step-by-step transformation” is shown.

- Output: final PDF draft + final PDF.

- Depends on all.

Andrew (diagram-heavy moderate/simple contributions + CRC + communication diagrams)

Part 1 — Simple Use Case Design (CRC)

B1 – CRC for 2 Simple Use Cases (with view + data layer classes)

Do CRC cards (PowerPoint is fine) for 2 simple UCs.

Must include boundary/view + controller + domain + DAO responsibilities.

Output: CRC slides + list of discovered methods.

Depends on A0 + A2/A3.

B2 – Update First-Cut Diagram Partition Notes (Feedback to Adham)

Validate that chosen classes match CRC findings.

Output: change suggestions list.

Depends on B1.

Part 2 — Moderate Use Case Design (Communication Diagrams)

B3 – Communication Diagrams for 2 Moderate Use Cases

Multi-layer communication diagrams: view objects → controller → domain → DAO.

Output: 2 communication diagrams + method/message list.

Depends on A0 + A2/A3.

Ahmed (system/data focus: DB-heavy UCs, DAO correctness, communication diagrams)

Part 1 — Moderate Use Cases (DB/system-heavy)

C1 – Communication Diagrams for 2 Moderate Use Cases (system/DB heavy)

- Choose moderate UCs with database CRUD and validations.

- Output: 2 communication diagrams + method list.

- Depends on A0 + A2/A3.

Part 2 — Implementation Support (Data Layer owner)

C2 – DAO + Database Schema Draft (aligned to design class diagram)

- Propose tables + primary keys + relationships + CRUD mapping.

- Output: ERD/table schema + DAO method signatures.

- Depends on A2; should be consistent with A5 eventually.

C3 – Support Adham in implementing 2 simple DB use cases

- Implement DAOs + SQL queries + test data seeds.

- Output: DAO classes + tested CRUD.

- Depends on A8 direction + C2.

Yassin (quality control + coordination: Jira/GitHub + validation + diagram consistency)

Part 0 — Project Management

D1 – Jira Timeline Setup + Dependencies

- Create Jira epics aligned to:

  - Use case selection/classification

  - First-cut DCD

  - Simple CRC

  - Moderate communication

  - Complex sequence

  - Final DCD + package

  - Model-to-code

  - Implement 2 simple UCs

  - Final PDF + submission bundle

- Output: Jira board with tasks A*/B*/C*/D* and dependency links.

- Depends on this plan (can start immediately).

D2 – GitHub Organization + Submission Bundle Owner

- Repo structure:

  - /docs (PDF + diagrams exports)

  - /uml (tool project files zipped)

  - /java (code)

- Output: clean repo structure + submission zip(s).

- Depends on ongoing work; finalized at end.

Part 1 — Validation & Consistency

D3 – Consistency Check: 12 Use Cases vs Diagrams vs Design Classes

- Verify each of the 12 UCs has:

  - a realization artifact (CRC/comm/sequence)

  - methods reflected in final DCD

  - correct layering rules

- Output: checklist + issues list.

- Depends on A5 draft.

D4 – Final Diagram Review Pass (before PDF freeze)

- Naming consistency, method completeness, layer boundaries.

- Output: “ready to submit” sign-off or fix list.

- Depends on A9 draft.

Submission

Deliverables Checklist (what you must submit)

- PDF Technical Report (A9 owner, inputs from everyone)

- UML project files (zipped)

- Final Design Class Diagram (A5)

- Package Diagram (A6)

- CRC artifacts for simple UCs (B1)

- Communication diagrams for moderate UCs (B3 + C1)

- Sequence diagrams for complex UCs (A4)

- Java Project

  - model-to-code skeleton (A7)

  - 2 simple DB use cases implemented in 3 layers + D4 UI included (A8 + C3)

- Jira timeline (D1) + GitHub organized repo (D2)