Adham (Leader – hardest/most central: project backbone + Java architecture + integration)

Part 0 — Foundation (everyone depends on this)

- A0 – Confirm Project Baseline + DevOps Compliance Snapshot

  - Open the existing project from:

A:\Introduction-To-Software-Engineering-Project\Introduction-To-Software-Engineering-Project

  - Confirm it builds/runs in NetBeans/Eclipse using Maven.

  - Confirm Git repo status (branches strategy) and confirm JIRA project exists.

  - Output: “baseline checklist” (build OK / run OK / Maven OK / Git OK / JIRA OK) + any assumptions.

  - Everyone depends on A0.

- A1 – Create Deliverable #1 “Master Template” for the Technical Report (PDF structure)

  - Set report sections + numbering matching requirements:

    - Automated Java Code Generation (status)

    - Identified pattern cases (Singleton/Factory Method/Abstract Factory)

    - UML diagrams per case

    - Implementation confirmation (no code in report)

    - Assumptions

  - Output: report skeleton + where each UML diagram goes.

  - Depends on A0.

Part 1 — Pattern Selection (final decision owner + tie-breaker)

- A2 – Finalize the Official List of Required Cases (the “frozen scope”)

  - Freeze exactly:

    - 2 Singleton cases

    - 1 Factory Method case

    - 2 Abstract Factory cases

  - Resolve overlaps/duplicate ideas and ensure each case is clearly different.

  - Output: final “cases list” with 1–2 lines per case.

  - Depends on B1 + B2 + M1 + D1.

- A3 – Integration Gate: “Team Implementation Rules” (to avoid merge chaos)

  - Naming conventions, package structure rules, where patterns live, and how to test/run.

  - Example: ui/, controller/, domain/, dao/, util/, factory/ (or whatever matches your project).

  - Output: 1-page implementation rules used by everyone.

  - Depends on A0.

Part 2 — Abstract Factory (hardest design + central integration)

- A4 – Abstract Factory Case #1: UML Class Diagram + Rationale

  - Create UML class diagram that conceptually illustrates the proposed solution.

  - Output: UML diagram + 5–8 lines rationale.

  - Depends on A2.

- A5 – Abstract Factory Case #2: UML Class Diagram + Rationale

  - Create UML class diagram that conceptually illustrates the proposed solution.

  - Output: UML diagram + 5–8 lines rationale.

  - Depends on A2.

Part 3 — Final Merge Owner + Final PDF Owner

- A6 – Full Build/Run Gate + Merge Conflict Resolution (final integration owner)

  - Merge Andrew + Yassin + Maged branches, fix conflicts, ensure build + run is clean.

  - Output: final integrated code state (tag/commit ready for submission).

  - Depends on B4 + Y1 + M2 + D4 + A5 + D2.

- A7 – Technical Report Integration (Final PDF Owner)

  - Merge all writeups + all UML diagrams into the final PDF.

  - Ensure assumptions are explicit and “no code included” is respected.

  - Output: final PDF.

  - Depends on A1 + B5 + Y3 + M3 + D5 + A4 + A5.

- A8 – Submission Readiness Checklist (final sign-off)

  - Confirm submission components exist and are correct (PDF + NetBeans project + DevOps evidence).

  - Output: “ready to submit” checklist signed by leader.

  - Depends on A6 + A7 + D6.

Andrew (diagram-heavy + implementation-heavy for part of patterns)

Part 1 — Case Discovery + UML Production (you generate clean diagrams + rationale drafts)

- B1 – Singleton: Identify 2 Cases/Problems + Justification Draft

  - Propose 2 realistic singleton cases from the existing project.

  - Output: 2 case statements + justification bullets.

  - Depends on A0.

- B2 – Factory Method: Identify 1 Case/Problem + Justification Draft

  - Propose 1 factory method case from existing project.

  - Output: case statement + justification bullets.

  - Depends on A0.

- B3 – UML Class Diagrams for Andrew-owned Cases

  - Singleton Case #1 UML

  - Singleton Case #2 UML

  - Factory Method UML

  - Output: 3 UML class diagrams + brief rationale text for each.

  - Depends on B1 + B2 + A3.

Part 2 — Implementation (pattern coding owner for part of patterns)

- B4 – Implement Singleton Case #1 in Java

  - Implement Singleton Case #1 cleanly in the existing project.

  - Must compile and run with no errors.

  - Output: working implementation merged-ready.

  - Depends on B3 + A3 + D2.

Part 3 — Report Contributions

- B5 – Write Report Sections for: Singleton Case #1

  - Describe the case/problem and why the pattern solves it.

  - Reference the UML diagram.

  - Output: report-ready text + exported diagram.

  - Depends on B3 (diagrams finalized) + B4 (implementation done).

Yassin (balanced: project management + implementation + QA)

Part 0 — Project Management (dependencies + tracking)

- D1 – JIRA Timeline Setup + Dependencies (mirror A/B/M/D)*

  - Create epics/tasks aligned to: foundation, case selection, UML, implementation, report, submission.

  - Add dependency links exactly like “depends on …”.

  - Output: JIRA board with tasks A*/B*/M*/D* and dependency links.

  - Depends on this plan (can start immediately).

- D2 – Git Organization + Branch Strategy Enforcement (repo hygiene)

  - Ensure: branches per owner, PR rules, commit naming, and a clean structure for docs/uml/java.

  - Output: clean repo structure + PR flow working.

  - Depends on A0.

Part 1 — Implementation (now owns one pattern to balance workload)

- Y1 – Implement Singleton Case #2 in Java

  - Implement Singleton Case #2 cleanly in the existing project.

  - Must compile and run with no errors.

  - Output: working implementation merged-ready.

  - Depends on B3 (UML ready) + A3 (rules) + D2 (Git ready).

Part 2 — Validation (correctness + completeness gatekeeper)

- D3 – Consistency Check: Requirements vs What We Produced

  - Verify deliverable requirements are satisfied:

    - 2 Singleton cases

    - 1 Factory Method case

    - 2 Abstract Factory cases

    - UML diagram for each case

    - Implementation exists and runs

    - DevOps tech mentioned/used (Git, Maven, JIRA, IDE)

  - Output: checklist + issues list.

  - Depends on A2 (cases frozen) + B3 + A4 + A5.

- D4 – Final “Runs With No Errors” Verification Pass

  - Pull latest integrated code (or test PR branches if needed) and verify compile/run.

  - Output: pass/fail + exact errors if fail.

  - Depends on B4 + Y1 + M2 + A5.

Part 3 — Report QA + Submission Packaging

- D5 – Diagram & Text QA Pass (before PDF freeze)

  - Naming consistency, pattern correctness, diagram readability, report formatting consistency.

  - Output: “ready to freeze” sign-off or fix list.

  - Depends on B5 + Y3 + M3 + A4 + A5.

- D6 – Submission Bundle Owner (ZIPs + folder structure + final artifacts)

  - Prepare submission bundle(s):

    - PDF Technical Report

    - NetBeans project (complete runnable)

    - UML project files (zipped)

    - Exported UML diagrams used in report

  - Output: final ZIP(s) ready for Canvas upload.

  - Depends on A7 (final PDF) + A6 (final integrated code) + D5.

Part 4 — Report Contributions

- Y3 – Write Report Section for: Singleton Case #2

  - Describe the case/problem and why the pattern solves it.

  - Reference the UML diagram.

  - Output: report-ready text + exported diagram.

  - Depends on B3 (diagram finalized) + Y1 (implementation done).

Maged (balanced: implementation + report + QA)

Part 0 — Case Discovery (shared with Andrew for equal workload)

- M1 – Abstract Factory: Identify 2 Cases/Problems + Justification Draft

  - Propose 2 realistic Abstract Factory cases from the existing project.

  - Output: 2 case statements + justification bullets.

  - Depends on A0.

Part 1 — Implementation (owns one Abstract Factory case to balance workload)

- M2 – Implement Abstract Factory Case #1 in Java

  - Implement Abstract Factory Case #1 cleanly in the existing project.

  - Must compile and run with no errors.

  - Output: working implementation merged-ready.

  - Depends on A4 (UML ready) + A3 (rules) + D2 (Git ready).

Part 2 — Report Contributions

- M3 – Write Report Sections for: Abstract Factory Case #1 + Factory Method

  - Describe the cases/problems and why the pattern solves them.

  - Reference the UML diagrams.

  - Output: report-ready text + exported diagrams.

  - Depends on A4 (diagram finalized) + M2 (implementation done) + B2 (Factory Method case).